## Start Here
Contractor Estimate and Invoice
Enter the job once on Details and Items. The Estimate and Invoice sheets fill themselves in, ready to print or save as PDF.
KEY METRICS |  |  | HOW TO USE THIS TEMPLATE
Metric | Value | Notes
Estimate Total | 8328.86 | Including discount and tax. |  | Pale yellow: type your own data here.
Invoice Total | 8683.96 | Uses Actual Qty where you entered one. |  | Green: formulas that update on their own. Don't type over them.
Change vs Estimate | 355.1 | Invoice total less estimate total. | ▾ | Dropdown arrow: pick from the list. Edit the choices on the Lists tab.
Balance Due | 5683.96 | Invoice total less payments received. | ! | Checks tab: Review means something needs a look.
Due Date | 2026-11-12 | Invoice date plus the payment terms. | → | Step-by-step guide: arumsoft.com/resources
Markup Earned | 488.79 | Invoice amounts less your cost, before discount. |  | Checks needing review | 0 | All clear
WORKBOOK NAVIGATION |  |  | INVOICE BY ITEM TYPE
Sheet (click to open) | What it's for |  | Type |  | Amount
Details | Your business, client, job, numbers, tax and markup. |  | Labor |  | 4720
Items | Line items with quantities, costs and markup. |  | Materials |  | 3072.29
Estimate | Print-ready estimate (one page). |  | Equipment |  | 247.5
Invoice | Print-ready invoice (one page). |  | Subcontract |  | 715
Lists | Edit types, units and payment terms. |  | Other |  | 175
Checks | Review flags before sending.

## Details
Details
Your business, the client, the job, numbering, tax and markup. Everything on the Estimate and Invoice comes from here and the Items sheet.
YOUR BUSINESS |  | MARKUP BY ITEM TYPE
Business name | Northline Home Renovations | Type → markup % added to your cost
Street address | 418 Cedar Lane | Labor | 0%
City, state and ZIP | Maple Grove, MN 55311 | Materials | 15%
Phone | (555) 014-2290 | Equipment | 10%
Email | office@example.com | Subcontract | 10%
License or tax ID | Lic. #BC-204817 | Other | 0%
CLIENT |  | Labor is usually 0% because your hourly rate already includes your margin.
Client name | Dana Whitfield
Street address | 27 Orchard Street
City, state and ZIP | Maple Grove, MN 55311
Phone | (555) 018-7741
Email | dana.w@example.com
JOB
Job name | Hall bathroom remodel
Job site address | 27 Orchard Street, Maple Grove
Description of work | Remove the existing tub and tile. Install a walk-in shower with a glass door, new vanity, toilet and vinyl plank flooring. Add a fan and lighting circuit, then paint and finish trim.
ESTIMATE
Estimate number | EST-0318
Estimate date | 2026-10-12
Valid for (days) | 30
Deposit required to start | 30%
INVOICE
Invoice prefix | INV-
Invoice number | 1042
Invoice date | 2026-10-28
Payment terms | Net 15
Deposit received | 3000
Other payments received | 0
TAX AND DISCOUNT
Sales tax rate (on taxable lines) | 6.875%
Discount on this job | 5%
NOTES
Estimate notes and terms | Price includes labor, materials and cleanup. Changes to the scope are quoted separately. A 30% deposit is due to schedule the work.
Payment instructions | Pay by check to Northline Home Renovations or by bank transfer. Please include the invoice number with your payment.

## Items
Items
One row per line item. Est. Qty goes on the Estimate. Add Actual Qty when the job is done and the Invoice uses it instead.
Type | Description | Unit | Est. Qty | Cost / Unit | Markup % | Price / Unit | Estimate Amount | Actual Qty | Invoice Qty | Invoice Amount | Taxable | Notes
Labor | Demolition and haul-away | hr | 12 | 65 | 0% | 65 | 780 | 14 | 14 | 910 | No
Labor | Plumbing rough-in and fixture install | hr | 16 | 85 | 0% | 85 | 1360 | 18 | 18 | 1530 | No
Labor | Tile installation, shower and floor | hr | 24 | 70 | 0% | 70 | 1680 |  | 24 | 1680 | No
Labor | Paint and finish carpentry | hr | 10 | 60 | 0% | 60 | 600 |  | 10 | 600 | No
Materials | Shower tile and setting materials | sq ft | 120 | 7.5 | 15% | 8.63 | 1035.6 | 128 | 128 | 1104.64 | Yes
Materials | Glass shower door | ea | 1 | 680 | 15% | 782 | 782 |  | 1 | 782 | Yes
Materials | Vanity with top | ea | 1 | 540 | 15% | 621 | 621 |  | 1 | 621 | Yes
Materials | Toilet | ea | 1 | 260 | 15% | 299 | 299 |  | 1 | 299 | Yes
Materials | Vinyl plank flooring | sq ft | 55 | 4.2 | 15% | 4.83 | 265.65 |  | 55 | 265.65 | Yes
Equipment | Dumpster rental | day | 5 | 45 | 10% | 49.5 | 247.5 |  | 5 | 247.5 | No
Subcontract | Electrician: fan and lighting circuit | lot | 1 | 650 | 10% | 715 | 715 |  | 1 | 715 | No
Other | Building permit | ea | 1 | 175 | 0% | 175 | 175 |  | 1 | 175 | No

## Estimate
Northline Home Renovations |  |  |  |  | ESTIMATE
418 Cedar Lane |  |  |  | Estimate # | EST-0318
Maple Grove, MN 55311 |  |  |  | Date | 2026-10-12
(555) 014-2290 · office@example.com |  |  |  | Valid until | 2026-11-11
Lic. #BC-204817
PREPARED FOR |  |  | JOB SITE
Dana Whitfield |  |  | Hall bathroom remodel
27 Orchard Street |  |  | 27 Orchard Street, Maple Grove
Maple Grove, MN 55311
(555) 018-7741
dana.w@example.com
DESCRIPTION OF WORK
Remove the existing tub and tile. Install a walk-in shower with a glass door, new vanity, toilet and vinyl plank flooring. Add a fan and lighting circuit, then paint and finish trim.
# | Description | Qty | Unit | Unit Price | Amount
1 | Demolition and haul-away | 12 | hr | 65 | 780
2 | Plumbing rough-in and fixture install | 16 | hr | 85 | 1360
3 | Tile installation, shower and floor | 24 | hr | 70 | 1680
4 | Paint and finish carpentry | 10 | hr | 60 | 600
5 | Shower tile and setting materials | 120 | sq ft | 8.63 | 1035.6
6 | Glass shower door | 1 | ea | 782 | 782
7 | Vanity with top | 1 | ea | 621 | 621
8 | Toilet | 1 | ea | 299 | 299
9 | Vinyl plank flooring | 55 | sq ft | 4.83 | 265.65
10 | Dumpster rental | 5 | day | 49.5 | 247.5
11 | Electrician: fan and lighting circuit | 1 | lot | 715 | 715
12 | Building permit | 1 | ea | 175 | 175
NOTES AND TERMS |  |  |  | Subtotal | 8560.75
Price includes labor, materials and cleanup. Changes to the scope are quoted separately. A 30% deposit is due to schedule the work. |  |  | 5% | Discount | -428.04
|  |  | 6.875% | Tax | 196.15
|  |  |  | Total | 8328.86
|  |  | 30% | Deposit to start | 2498.66
Accepted by: ______________________________ |  |  |  | Date: ______________
To accept, sign and return this estimate with the deposit. Thank you for the opportunity to quote this job.

## Invoice
Northline Home Renovations |  |  |  |  | INVOICE
418 Cedar Lane |  |  |  | Invoice # | INV-1042
Maple Grove, MN 55311 |  |  |  | Invoice date | 2026-10-28
(555) 014-2290 · office@example.com |  |  |  | Due date | 2026-11-12
Lic. #BC-204817 |  |  |  | Terms | Net 15
BILL TO |  |  | JOB SITE
Dana Whitfield |  |  | Hall bathroom remodel
27 Orchard Street |  |  | 27 Orchard Street, Maple Grove
Maple Grove, MN 55311
(555) 018-7741
dana.w@example.com
DESCRIPTION OF WORK
Remove the existing tub and tile. Install a walk-in shower with a glass door, new vanity, toilet and vinyl plank flooring. Add a fan and lighting circuit, then paint and finish trim.
# | Description | Qty | Unit | Unit Price | Amount
1 | Demolition and haul-away | 14 | hr | 65 | 910
2 | Plumbing rough-in and fixture install | 18 | hr | 85 | 1530
3 | Tile installation, shower and floor | 24 | hr | 70 | 1680
4 | Paint and finish carpentry | 10 | hr | 60 | 600
5 | Shower tile and setting materials | 128 | sq ft | 8.63 | 1104.64
6 | Glass shower door | 1 | ea | 782 | 782
7 | Vanity with top | 1 | ea | 621 | 621
8 | Toilet | 1 | ea | 299 | 299
9 | Vinyl plank flooring | 55 | sq ft | 4.83 | 265.65
10 | Dumpster rental | 5 | day | 49.5 | 247.5
11 | Electrician: fan and lighting circuit | 1 | lot | 715 | 715
12 | Building permit | 1 | ea | 175 | 175
PAYMENT INSTRUCTIONS |  |  |  | Subtotal | 8929.79
Pay by check to Northline Home Renovations or by bank transfer. Please include the invoice number with your payment. |  |  | 5% | Discount | -446.49
|  |  | 6.875% | Tax | 200.66
|  |  |  | Total | 8683.96
|  |  |  | Less deposit received | -3000
|  |  |  | Less other payments | 0
|  |  |  | Balance due | 5683.96
Thank you for your business.
Questions about this invoice? Contact (555) 014-2290 or office@example.com.

## Lists
Lists
Dropdown choices used across the workbook. Add, rename or remove items here and the dropdowns update.
Item Types | Units | Yes / No | Payment Terms | Terms Days
Labor | hr | Yes | Due on receipt | 0
Materials | ea | No | Net 7 | 7
Equipment | sq ft |  | Net 15 | 15
Subcontract | ln ft |  | Net 30 | 30
Other | day
lot
gal
box
Item Types feed the markup table on Details (5 types). Terms Days is the number of days after the invoice date that payment is due.

## Checks
Checks
Quick review flags before you send an estimate or invoice.
Check | Status | Where to Fix
Every line item has a type | OK | Items: Type
Every line item has a quantity and a cost | OK | Items: Est. Qty and Cost / Unit
Every line item says whether it is taxable | OK | Items: Taxable
Client name is filled in | OK | Details: Client name
Tax rate and discount are between 0% and 100% | OK | Details: Tax and discount
Payments received are not more than the invoice total | OK | Details: Deposit received
Invoice is not past due | OK | Invoice: Due date and Balance due
OK means the check passed. Review means something needs a look: open the sheet named in Where to Fix.