## Start Here
Gantt Chart Maker
Type tasks with a start date and duration. The Gantt bars, end dates and progress update on their own.
KEY METRICS |  |  | HOW TO USE THIS TEMPLATE
Metric | Value | Notes
Tasks | 10 | Rows with a task name, not counting milestones. |  | Pale yellow: type your own data here.
Milestones | 3 | Rows with Type set to Milestone. |  | Green: formulas that update on their own. Don't type over them.
Project Start | 2026-10-05 | Earliest start date. | ▾ | Dropdown arrow: pick from the list. Edit the choices on the Lists tab.
Project Finish | 2026-12-16 | Latest end date. | ! | Checks tab: Review means something needs a look.
Overall Progress | 38.64% | % complete weighted by each task's duration. | → | Step-by-step guide: arumsoft.com/resources
Late Tasks | 1 | Past the end date and not 100% complete. |  | Checks needing review | 1 | Open the Checks tab
WORKBOOK NAVIGATION |  |  | PROGRESS BY PHASE
Sheet (click to open) | What it's for |  | Phase |  | Progress
Tasks | List tasks, owners, start dates and durations. |  | Plan |  | 100%
Gantt | See the bars on a daily or weekly timeline. |  | Design |  | 65%
Lists | Edit phases, owners and dropdown values. |  | Build |  | 27.42%
Checks | Review schedule flags. |  | Test |  | 0%
|  |  | Launch |  | 0%
|  |  | Wrap-up |  | 0%

## Tasks
Tasks
Enter one row per task or milestone. End dates, status and the Gantt bars are calculated.
|  |  |  | Duration counts → | Calendar days
Phase | Task | Owner | Type | Start | Duration (days) | End | % Complete | Status | Notes
Plan | Project kickoff | Avery | Milestone | 2026-10-05 |  | 2026-10-05 | 100% | Complete
Plan | Gather requirements | Avery | Task | 2026-10-05 | 7 | 2026-10-11 | 100% | Complete
Plan | Sitemap and content plan | Jordan | Task | 2026-10-12 | 5 | 2026-10-16 | 100% | Complete
Design | Wireframes | Jordan | Task | 2026-10-16 | 10 | 2026-10-25 | 100% | Complete
Design | Visual design | Sam | Task | 2026-10-23 | 14 | 2026-11-05 | 40% | In Progress
Design | Design sign-off | Avery | Milestone | 2026-11-06 |  | 2026-11-06 | 0% | Not Started
Build | Set up hosting and CMS | Riley | Task | 2026-10-19 | 7 | 2026-10-25 | 60% | Late
Build | Write and load content | Morgan | Task | 2026-10-19 | 35 | 2026-11-22 | 35% | In Progress
Build | Build page templates | Riley | Task | 2026-11-09 | 18 | 2026-11-26 | 0% | Not Started
Test | QA and bug fixes | Sam | Task | 2026-11-27 | 10 | 2026-12-06 | 0% | Not Started
Test | Accessibility review | Morgan | Task | 2026-12-01 | 5 | 2026-12-05 | 0% | Not Started
Launch | Go-live | Avery | Milestone | 2026-12-08 |  | 2026-12-08 | 0% | Not Started
Wrap-up | Post-launch review | Jordan | Task | 2026-12-14 | 3 | 2026-12-16 | 0% | Not Started
Formulas:
End = IF(OR([Task]="",[Start]=""),"",IF([Type]="Milestone",[Start],IF(F3="Workdays",WORKDAY([Start],MAX(1,N([Duration (days)]))-1),[Start]+MAX(1,N([Duration (days)]))-1)))
Status = IF([Task]="","",IF(N(H5)>=1,"Complete",IF(AND([End]<>"",[End]<TODAY()),"Late",IF(N(H5)>0,"In Progress","Not Started"))))

## Gantt
Gantt Chart
Dark green = done, light green = still to do, ◆ = milestone, red column = today. Set the first date and the scale in row 3.
Timeline starts on → | 2026-10-05 | Scale → | Week |  | 2026-10-05 |  |  |  | 2026-11-02 |  |  |  |  | 2026-12-07 |  |  |  | 2027-01-04 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  |  | 2027-06-07 |  |  |  | 2027-07-05 |  |  |  | 2027-08-02 |  |  |  |  | 2027-09-06
Task | Owner | Start | End | % | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27
◆ Project kickoff | Avery | 2026-10-05 | 2026-10-05 | 100% | ◆
Gather requirements | Avery | 2026-10-05 | 2026-10-11 | 100% | d
Sitemap and content plan | Jordan | 2026-10-12 | 2026-10-16 | 100% |  | d
Wireframes | Jordan | 2026-10-16 | 2026-10-25 | 100% |  | d | d
Visual design | Sam | 2026-10-23 | 2026-11-05 | 40% |  |  | d | d | r
◆ Design sign-off | Avery | 2026-11-06 | 2026-11-06 | 0% |  |  |  |  | ◆
Set up hosting and CMS | Riley | 2026-10-19 | 2026-10-25 | 60% |  |  | d
Write and load content | Morgan | 2026-10-19 | 2026-11-22 | 35% |  |  | d | d | r | r | r
Build page templates | Riley | 2026-11-09 | 2026-11-26 | 0% | [5 empty] | r | r | r
QA and bug fixes | Sam | 2026-11-27 | 2026-12-06 | 0% | [7 empty] | r | r
Accessibility review | Morgan | 2026-12-01 | 2026-12-05 | 0% | [8 empty] | r
◆ Go-live | Avery | 2026-12-08 | 2026-12-08 | 0% | [9 empty] | ◆
Post-launch review | Jordan | 2026-12-14 | 2026-12-16 | 0% | [10 empty] | r

## Lists
Lists
Dropdown choices used across the workbook. Add, rename or remove items here and the dropdowns update.
Phases | Owners | Types | Scale | Duration Counts
Plan | Avery | Task | Day | Calendar days
Design | Jordan | Milestone | Week | Workdays
Build | Sam
Test | Riley
Launch | Morgan
Wrap-up
Types, Scale and Duration Counts are used by formulas, so keep those words as they are. Phases and Owners can be edited freely.

## Checks
Checks
Quick review flags for the schedule.
Check | Status | Where to Fix
Every task has a start date | OK | Tasks: Start
Every task has a duration (milestones excepted) | OK | Tasks: Duration (days)
Every task has an owner | OK | Tasks: Owner
% Complete is between 0% and 100% | OK | Tasks: % Complete
No late tasks | Review | Tasks: filter Status to Late
The whole project fits on the Gantt sheet | OK | Gantt: change B3 or switch the scale to Week
OK means the check passed. Review means something needs a look: open the sheet named in Where to Fix.