## Start Here
Project and Task Tracker
Track tasks, owners, due dates, progress, and project budget status.
KEY METRICS |  |  | HOW TO USE THIS TEMPLATE
Metric | Value | Notes
Total Tasks | 4 | Tasks with a task name. |  | Pale yellow: type your own data here.
Open Tasks | 3 | Not started, in progress or blocked. |  | Green: formulas that update on their own. Don't type over them.
Overdue Tasks | 0 | Open tasks past due. | ▾ | Dropdown arrow: pick from the list. Edit the choices on the Lists tab.
Complete Tasks | 1 | Tasks marked complete. | ! | Checks tab: Review means something needs a look.
Average Progress | 56.25% | Average completion across populated tasks. | → | Step-by-step guide: arumsoft.com/resources
Budget Variance | 12000 | Budget less actual cost. |  | Checks needing review | 0 | All clear
WORKBOOK NAVIGATION |  |  | TASKS BY STATUS
Sheet (click to open) | What it's for |  | Status |  | Tasks
Tasks | Log every task, owner, due date, and status. |  | Not Started |  | 1
Projects | Track budget, actuals, and rollup progress. |  | In Progress |  | 2
Timeline | View a simple monthly timeline. |  | Blocked |  | 0
Lists | Edit dropdown values. |  | Complete |  | 1
Checks | Review risk flags.

## Tasks
Tasks
Enter one row per task.
Project | Task | Owner | Priority | Status | Start | Due | % Complete | Flag | Notes
Website Refresh | Finalize sitemap | Avery | High | Complete | 2026-10-01 | 2026-10-05 | 100% | OK
Website Refresh | Design product pages | Jordan | High | In Progress | 2026-10-06 | 2026-10-20 | 55% | OK
Website Refresh | QA launch checklist | Sam | Medium | Not Started | 2026-10-21 | 2026-10-28 | 0% | OK
CRM Cleanup | Merge duplicate accounts | Riley | Medium | In Progress | 2026-10-03 | 2026-10-18 | 70% | OK
Formulas:
Flag = IF([Task]="","",IF([Status]="Complete","OK",IF([Due]<TODAY(),"Overdue","OK")))

## Projects
Projects
Track project-level budget and progress.
Project | Sponsor | Start | Due | Budget | Actual Cost | Variance | Progress | Notes
Website Refresh | Marketing | 2026-10-01 | 2026-10-31 | 15000 | 6200 | 8800 | 51.67%
CRM Cleanup | Sales Ops | 2026-10-03 | 2026-11-15 | 5000 | 1800 | 3200 | 70%

## Timeline
Timeline
Simple monthly timeline driven by the Tasks sheet.
|  |  | First month → | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Project | Task | Owner | Status | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Website Refresh | Finalize sitemap | Avery | Complete | bar: 2026-10-01
Website Refresh | Design product pages | Jordan | In Progress | bar: 2026-10-01
Website Refresh | QA launch checklist | Sam | Not Started | bar: 2026-10-01
CRM Cleanup | Merge duplicate accounts | Riley | In Progress | bar: 2026-10-01

## Lists
Lists
Dropdown choices used across the workbook. Add, rename or remove items here and the dropdowns update.
Priority | Status | Owners
High | Not Started | Avery
Medium | In Progress | Jordan
Low | Blocked | Sam
| Complete | Riley

## Checks
Checks
Quick review flags for task risk.
Check | Status | Where to Fix
No overdue tasks | OK | Tasks
Every task has an owner | OK | Tasks
Every task has a due date | OK | Tasks
Project budgets are not exceeded | OK | Projects
OK means the check passed. Review means something needs a look: open the sheet named in Where to Fix.