## Slide 1: Q3 planning kickoff
Tuesday, June 9, 2026 · 10:00–11:00 · Room 4B and video · Facilitator: Omar Haddad · Note-taker: Chloe Martin
Product team

## Slide 2: Agenda
Time | Item | Owner | Purpose
10:00 | Q2 results and what we learned | Omar | Inform
10:15 | Q3 objectives: proposal | Sofia | Decide
10:35 | Capacity and hiring | Aiko | Discuss
10:50 | Risks and dependencies | All | Discuss
10:58 | Actions and next meeting | Chloe | Confirm
Attendees: Omar Haddad, Sofia Rossi, Aiko Tanaka, Chloe Martin, Liam Walsh. Apologies: Daniel Kim.

## Slide 3: Discussion notes
Q2 results
Shipped 7 of 9 planned features. Activation up 9 points after onboarding redesign. Two features slipped because of the data-pipeline migration.
Q3 objectives
Proposal: (1) self-serve import, (2) team workspaces, (3) reliability to 99.9%. Debate on whether workspaces fit in one quarter; agreed to scope to 'shared folders' first.
Capacity
Two engineers on the pipeline migration until mid-July. One open backend role; recruiter has 4 candidates in final stage.
Risks
Workspaces depend on the auth refactor (platform team). Import depends on the new file service landing by June 30.

## Slide 4: Decisions
1
Q3 objectives approved
Self-serve import, shared folders (not full workspaces), 99.9% reliability. Owner: Sofia.
2
Shared folders scoped to read/write, no permissions UI in Q3
Permissions move to Q4 backlog. Owner: Omar.
3
Backfill decision deferred
Decide on the open backend role after the pipeline migration lands (July 15 check-in).

## Slide 5: Action items
Action | Owner | Due | Status
Write Q3 objectives one-pager and share with leadership | Sofia | Jun 12 | Open
Confirm auth refactor timeline with the platform team | Aiko | Jun 16 | Open
Draft shared-folders scope and success metric | Omar | Jun 19 | Open
Schedule July 15 capacity check-in | Chloe | Jun 10 | Done
Send minutes to the team | Chloe | Jun 9 | Done
Next meeting: Tuesday, June 23, 10:00. Agenda owner: Omar.