## Slide 1: OKR review: Q3 2026
Northgate Health · Patient Services · Week 10 of 13 · Owner: Jordan Lee

## Slide 2: Scorecard: two objectives on track, one at risk
3
objectives
9
key results
6
on track
2
at risk
1
off track
Objective
Owner
Progress
Status
O1 · Patients get seen faster
Jordan
72%
On track
O2 · Fewer no-shows
Priya
48%
At risk
O3 · Staff stay
Marcus
85%
On track

## Slide 3: O1 · Patients get seen faster
KR1: Median wait for a first appointment from 21 to 10 days
Now 11 days · Start 21 · Target 10
70%
On track
KR2: 80% of urgent referrals seen within 48 hours (from 55%)
Now 76% · Start 55 · Target 80
84%
On track
KR3: Same-day phone triage live at all 6 clinics
Now 4 clinics · Start 0 · Target 6
67%
At risk
Triage rollout slipped at two clinics waiting on phone system upgrade (now scheduled Sept 18).

## Slide 4: O2 · Fewer no-shows
KR1: No-show rate from 14% to 8%
Now 11% · Start 14 · Target 8
50%
At risk
KR2: 90% of appointments confirmed by text (from 40%)
Now 71% · Start 40 · Target 90
62%
At risk
KR3: Waitlist auto-fill releases 500 slots a month
Now 180 slots · Start 0 · Target 500
36%
Off track
Auto-fill launched late (Aug 22). September data will show whether 500 is reachable; if not, retarget to 300.

## Slide 5: O3 · Staff stay
KR1: Nurse turnover under 12% annualized (from 19%)
Now 13% · Start 19 · Target 12
86%
On track
KR2: Every clinic runs a monthly staff forum
Now 6 clinics · Start 0 · Target 6
100%
On track
KR3: Pulse survey 'I would recommend working here' at 75% (from 61%)
Now 70% · Start 61 · Target 75
64%
On track
Turnover is trending down for the third straight quarter.

## Slide 6: KPI trend
Chart: 
| Apr | May | Jun | Jul | Aug | Sep
No-show rate (%) | 14 | 13.5 | 13 | 12.2 | 11.6 | 11
Urgent seen in 48h (%) | 55 | 58 | 63 | 68 | 72 | 76
Reading the chart
No-shows fall about 0.6 pts a month; 8% needs the auto-fill to work
Urgent-referral performance improved every month since triage pilots

## Slide 7: Decisions and asks
Item | Decision needed | Owner | By
O2 KR3 target | Keep 500 or retarget to 300 after September data | Priya | Oct 3
Phone upgrade | Approve $18k to bring forward the last two clinics | Jordan | Sep 12
Q4 objectives | Draft by Oct 10; review Oct 17 | All | Oct 17