## Slide 1: Warehouse management system rollout
Weekly status report · Week 14 · May 8, 2026 · Project manager: Lena Fischer
Harbor Logistics

## Slide 2: Overall status: on track, with one budget risk to watch
On track
Overall
Schedule
On track
Go-live still July 13
Budget
At risk
6% over on integration work
Scope
On track
No change requests this week
Risks
2 open
1 high, 1 medium
Summary
Receiving and put-away modules passed user testing this week with 94% of test cases green. Integration with the carrier API is running two weeks behind plan because of a vendor-side change; we have added a contractor and expect to recover one week by the end of May. Budget variance is driven by that extra integration work and is within the 10% contingency.

## Slide 3: Progress since last report
Done
Receiving and put-away UAT complete (94% pass; 3 defects open, none blocking)
Hired integration contractor; onboarded in two days
Pick-path optimization configured for Zone A
Training plan approved by operations
In progress
Carrier API integration (slipped from Apr 24)
Cycle-count module UAT
Zone B pick-path configuration
Chart: % complete, planned vs actual
| W8 | W9 | W10 | W11 | W12 | W13 | W14
Planned | 38 | 44 | 50 | 56 | 62 | 68 | 74
Actual | 37 | 43 | 48 | 53 | 58 | 63 | 69

## Slide 4: Milestones
Milestone | Planned | Forecast | Status
Design sign-off | Feb 20 | Feb 20 | Done
Receiving and put-away UAT | May 1 | May 6 | Done
Carrier API integration | Apr 24 | May 22 | Late
Cycle-count UAT | May 29 | May 29 | On track
End-to-end test | Jun 19 | Jun 19 | On track
Go-live | Jul 13 | Jul 13 | On track

## Slide 5: Risks and issues
Risk / issue | Impact | Likelihood | Owner | Response
Carrier API change delays integration | High | Occurred | P. Nair | Contractor added; weekly vendor call; fallback: manual label print for 2 weeks
Peak season starts before go-live | High | Low | L. Fischer | Go-live date fixed Jul 13; freeze scope from Jun 1
Warehouse staff training time | Medium | Medium | J. Berg | Train-the-trainer in June; floor walkers for 2 weeks after go-live

## Slide 6: Budget: 6% over plan, within contingency
Chart: Budget vs spent to date ($k)
| Software | Integration | Hardware | Training | PM
Budget | 180 | 120 | 95 | 40 | 65
Spent | 176 | 142 | 88 | 12 | 44
$500k
approved budget
$462k
spent to date
$530k
forecast at completion

## Slide 7: Next two weeks and decisions needed
Next two weeks
Complete carrier API mapping and run first live shipment (May 15)
Cycle-count UAT with inventory team (May 18–22)
Draft go-live runbook and rollback plan
Confirm hardware delivery dates for Zone B scanners
Decisions needed
Approve $30k contingency draw for integration contractor
Steering committee, May 12
Confirm two-week floor-walker support after go-live
Operations director, May 15